## Integration Plan
BUG_ID | pdk |  | Feature | TAG | S^N | Main Contributor | Package | IW0935 | IW0937 | IW0939 | IW0941 | IW0943 | IW0945 | IW0947 | IW0949 | IW0953 | xmad | IW1003 | IW1005 | IW1007 | IW1009 | IW1011 | IW1013 | 2010-Q2 | 2010-Q3 | 2010-Q4
246-8 | 2.0.0 |  | Additional Kernel components backport for S^3 to S^2 | N/A | S^2 | DOCOMO/SOSCO | Kernel & Hardware Services |  |  | 0 | [16 empty] | 1
| 3.0.a | -1 | New Comms Framework | 3PC | S^3 | NOKIA | Tech Domain Wide Features |  |  | 0 | [16 empty] | 1
| 3.0.a | -1 | 3PC architecture | 3PC | S^3 | NOKIA | Comms Framework |  |  | 0 | [16 empty] | 1
|  |  | SymbianJ | Java | S^3 | NOKIA | SymbianJ | [15 empty] | 1 |  |  |  | 1
1339 |  |  | NFC Server | NFC | S^4 | NOKIA | NFC | [19 empty] | 0
1340 |  |  | NFC Lib | NFC | S^4 | NOKIA | NFC | [19 empty] | 0
1341 |  |  | NFC Client | NFC | S^4 | NOKIA | NFC | [19 empty] | 0
906 | 3.0.f |  | volume control | AVRCP1.4 | S^3 | NOKIA | Btservices | [10 empty] | 0 | [8 empty] | 1
1347 | 3.0.f |  | Single click change | Singletap | S^3 | NOKIA | Files | [10 empty] | 0
1349 | 3.0.f |  | Contacts single click compatibility | Singletap | S^3 | NOKIA/IXONOS | Contacts | [8 empty] | 0
1345 | 3.0.f |  | Single Tap in S^3 | Singletap | S^3 | NOKIA | MusicPlayer | [8 empty] | 0
1348 | 3.0.f |  | Single Tap changes to Photos app in S^3. | Singletap | S^3 | NOKIA | Photos | [8 empty] | 0
1368 | 3.0.f |  | 'Single tap contribution' in Homescreen | Singletap | S^3 | NOKIA | Homescreen | [7 empty] | 0
1464 | 3.0.f |  | Single tap in organiser | Singletap | S^3 | NOKIA | Organiser | [7 empty] | 0
1397 |  |  | Single Tap in S^3 - Email UI | Singletap | S^3 | NOKIA | commonemail | [13 empty] | 2
739 | 3.0.f |  | Sinlge touch | Singletap | S^3 | NOKIA | ClassicUI | [7 empty] | 0
1451 |  |  | Make Qt 4.6.0 available to SF | NewUI | S^3 | NOKIA | QT | [8 empty] | 0 |  |  |  | 3
1452 |  |  | Ensure that Qt gitorious can be used as source for SF releases | NewUI | S^3 | NOKIA | QT | [12 empty] | 3
1453 |  |  | Ensure BC promise for Qt deliveries | NewUI | S^3 | NOKIA | QT | [13 empty] | 3
266 | 3.0.e |  | Homescreen page switching API | Multipage HS | S^3 | NOKIA | HomeScreen | [6 empty] | 0 | [12 empty] | 1
267 | 3.0.e |  | Homescreen mode switching API | Multipage HS | S^3 | NOKIA | HomeScreen | [6 empty] | 0 | [12 empty] | 1
268 | 3.0.d |  | Homescreen page management | Multipage HS | S^3 | NOKIA | HomeScreen | [5 empty] | 0 | [13 empty] | 1
208 |  |  | CalDav for single calendar | CalDav | S^3 | SUN | Organiser | [12 empty] | 2 | [6 empty] | 1
496 |  |  | CalDav for Multiple Calendar | CalDav | S^3 | SUN | Organiser | [19 empty] | 0
495 |  |  | Multiple Calendar | CalDav | S^3 | NOKIA | Organiser | [19 empty] | 0
599 | 3.0.f |  | RT+ Artist and Title support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [11 empty] | 1
600 | 3.0.f |  | RT+ Web support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [11 empty] | 1
601 | 3.0.f |  | Music Store support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [11 empty] | 1
565 | 3.0.e |  | Dialog reduction: A number of connection dialogs are removed from the software for better user experience. | dialog redux | S^3 | NOKIA | ipconmanagement | [5 empty] | 0 |  | 0 | [11 empty] | 2
438 | 3.0.f |  | Remote contact lookup | lookup | S^3 | NOKIA | Contacts | [8 empty] | 0 | [10 empty] | 1
420 |  |  | Music Playback over HDMI | HDMI | S^3 | NOKIA | Musicplayer | [12 empty] | 1 | [6 empty] | 1
466 | 3.0.f |  | Helix engine support for video files > 2GB | 2GB files | S^3 | NOKIA | Helix | [8 empty] | 0 | [10 empty] | 1
575 | 3.0.d |  | Support for files over 2GB | 2GB files | S^3 | NOKIA | imghandling | [5 empty] | 0 | [13 empty] | 1
587 | 3.0.d |  | Support for over 2GB files | 2GB files | S^3 | NOKIA | mds | [5 empty] | 0 | [13 empty] | 1
661 | 3.0.d |  | Local Location Based Triggering Enhancements | LBS | S^3 | NOKIA | Locationserv | [5 empty] | 0 | [13 empty] | 1
219 | N/A |  | Zoom2 Baseport | ExecEnv | S^3 | TI | BSP |  |  |  |  | 0 | [14 empty] | 1
179 | 3.0.d |  | NGA adaptation | NGA | S^3 | NOKIA | Telephony Apps | [5 empty] | 0 | [13 empty] | 1
182 | N/A |  | Basic Non-NGA Graphic Support | NGA | S^3 | NOKIA | Graphics |  |  | inFCL | [16 empty] | 1
235 |  | -1 | PC development platform | NGA | S^3 | NOKIA | Graphics | [12 empty] | 1 | [6 empty] | 1
181 | 3.0.f | -1 | Graphics surfaces and HW acceleration of graphics | NGA | S^3 | NOKIA | Graphics | [5 empty] | inFCL |  |  |  |  | 0 | [8 empty] | 2
1391 | ??? |  | UI Acceleration migration to OpenWF | NGA | S^3 | NOKIA | UIaccelerator | [11 empty] | 0
237 |  |  | Widget specific effects | NGA | S^3 | NOKIA | HomeScreen | [19 empty] | 0
238 | 3.0.f |  | Homescreen background animation | NGA | S^3 | NOKIA | UIaccelerator | [8 empty] | 0 | [10 empty] | 1
245 | 3.0.d |  | Symbian NGA support for video playback Link to feature description | NGA | S^3 | NOKIA | Video player |  |  |  | 0 | [15 empty] | 1
578 | 3.0.a |  | SMP prototype Kernel | SMP | S^3 | NOKIA | Kernel & Hardware Services |  |  | 0 | [16 empty] | 1
579 | 3.0.a |  | Writeable demand paging | WDP | S^3 | NOKIA | Kernel & Hardware Services |  |  | 0 | [16 empty] | 1
434 |  |  | Contacts application UI revolution using QT | NewUI | S^4 | NOKIA | Contacts | [16 empty] | 3 |  |  | 1
1469 |  |  | Make Qt 4.6.2 available for Symbian Foundation | NewUI | S^4 | NOKIA | QT | [15 empty] | 3
1470 |  |  | Make Qt 4.7 available for Symbian Foundation | NewUI | S^4 | NOKIA | QT | [16 empty] | 3
658 |  |  | Qt Location UI Apps | NewUI | S^4 | NOKIA | Location | [16 empty] | 3
624 |  |  | Conversation based messaging direct touch UI using Qt | NewUI | S^4 | NOKIA | Messaging
702 |  |  | Implementation of Access Security UIs with Qt | NewUI | S^4 | NOKIA | accesssec | [16 empty] | 3
560 |  |  | Qt-based Start up animation and splash screen | NewUI | S^4 | NOKIA | Generic_Applications_Support | [16 empty] | 3 |  |  | 1
826 |  |  | Direct UI | NewUI | S^4 | NOKIA | Phone | [16 empty] | 3 |  |  | 1
1111 |  |  | Support for the Bluetooth Low Energy Core Specification | Btlowenergy | S^4 | NOKIA | BT | [16 empty] | 3
zzz
[6 empty] | Package owner MCL bulk contribution |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 2 |  | 2 | 1 | 1 | 1 | 1 | 1 | Individual Package Contributions
|  |  | IW = integration Window |  | 0 | Done | [8 empty] | 0 | Planned contribution not recieved or not useable
|  |  | IW is a 2 week cycle at the end produces a PDK |  | 1 | Issue: Late or not committed | [8 empty] | 1 | Planned contribution in this time frame
[5 empty] | 2 | At risk | [8 empty] | 2 | Planned contribution recieved
|  |  | BUG_ID - Good engagement with contributor. Timeframe provided |  | 3 | Planned and on track
|  |  | BUG_ID - Engagement with contributor is pending |  | InFCL | FCL Drop Available | [9 empty] | -1 | "Heavy Duty" integration work
|  |  | BUG_ID - too far into the future to start engaging beyond backlog data |  | FCL | FCL Drop planned
Note on A25: victorp: ready to go, discussions on how to integrate it are holding it up
Note on S33: victorp: delivery date moved by 2 month
Note on U33: victorp: slip again, in test phase but no clear plan for delivery
Note on D36: victorp: recieved information that this has been done, checking with package owner when
Note on S42: victorp: Not all code in the FCL has made it to the MCL , possible distributionpolicy error in delivery

## Integration Graph
|  | 1 | 42 | 8
Column Labels
| Values | S^2 | S^3 | S^4 | Grand Total | Values | S^2 | S^3 | S^4
| Count of IW0935 |  |  |  |  | Count of IW0935 | 1 | 42
| Count of IW0937 |  |  |  |  | Count of IW0937 | 1 | 42
| Count of IW0939 | 1 | 5 |  | 6 | Count of IW0939 | 0 | 37
| Count of IW0941 |  | 1 |  | 1 | Count of IW0941 |  | 36
| Count of IW0943 |  | 1 |  | 1 | Count of IW0943 |  | 35
| Count of IW0945 |  | 7 |  | 7 | Count of IW0945 |  | 28
| Count of IW0947 |  | 2 |  | 2 | Count of IW0947 |  | 26
| Count of IW0949 |  | 7 |  | 7 | Count of IW0949 |  | 19
| Count of IW0953 |  | 7 |  | 7 | Count of IW0953 |  | 12
| Count of IW1003 |  | 3 |  | 3 | Count of IW1003 |  | 9
| Count of IW1005 |  | 1 |  | 1 | Count of IW1005 |  | 8
| Count of IW1007 |  | 5 |  | 5 | Count of IW1007 |  | 3
| Count of IW1009 |  | 2 |  | 2 | Count of IW1009 |  | 1 | 8
| Count of IW1011 |  |  |  |  | Count of IW1011 |  | 1 | 8
| Count of IW1013 |  | 1 | 1 | 2 | Count of IW1013 |  | 0 | 7
| Count of 2010-Q2 |  |  | 7 | 7 | Count of 2010-Q2 |  |  | 0
| Count of 2010-Q3 |  |  |  |  | Count of 2010-Q3 |  |  | 0
Count of 2010-Q4
| Non-SMP Safe SW | SMP SAFE SW Validated | Count N/A
os | 7 | 15 | 2 |  | 24
mw | 26 | 16 | 4 |  | 46
| Non-SMP Safe HW | SMP SAFE HW Validated | Count N/A
os | 9 | 11 | 4 |  | 24
mw | 37 | 7 | 2 |  | 46
OS | SW | HW
safe | 15 | 11
non-safe | 7 | 9
mw | SW&HW
safe | 16
non-safe | 26

## SMP List
| Done |  |  | S^3 Targets
| Still in progress |  |  | S^4 Targets
| Delayed / PkO unaware |  |  | S^5 Targets
SMP safe Status
| Package | Tech Domain | Layer | SMP Safe in Release | S/w based validation (Crazy scheduler) | H/w based validation (naviengine / bridge) | Comments
1 | boardsupport | OS Base services | OS | S^3 | Done | n/a | Emulator BSP - SMP validated for S^3, HAI - wont be affected by SMP Safe as per PkO
2 | buildtools | Tools | OS | S^3 | Done | n/a | Build tools are host side and hence h/w testing is not applicable.
3 | cellularsrv | Personal comms | OS | S^3 | Still work in progress |  | Except for CTSY, PkO aims to complete this by Q4. Wk 51: Pinged PkO for response
4 | commsfw | Data communication | OS | S^3 | Done | Done | PkO already confirmed this.
5 | deviceplatformrelease | Device Management | OS | S^3 | n/a | n/a | As per William Robert, SMP Safe may not apply for this package as its on the host side.
6 | devicesrv | OS Base services | OS | S^3 | Still work in progress |  | SW related components already validated for S^3, HW related components pending. Timeframe to be made available shortly. 4th Nov: PkO has written that h/w validation is targeted only by Q1/2010. Have asked for further clarification and notified about TB9.2 deadline. 16th Nov: PkO has been referred to MH/Nokia for h/w testing. Wk 51: Pinged pko again to ensure this happens within S^3 window.
7 | graphics | UI | OS | S^3 | Done | Done | Faisal Memon, the new PkO has already confirmed this.
8 | imagingext | Multimedia | OS | S^3 | Still work in progress (Jan 4th week would be the deadline) |  | PkO aims to complete this by wk 48, Wk 50: Asked for updates from package owners, updates are coming by for individual components. Have asked PkO to respond for the comp package. PkO has promised to come back by end of week 50. week 51: only one component validation pending - jan 4th week target
9 | kernelhwsrv | OS Base services | OS | S^3 | Done | Done | PkO already confirmed this.
10 | lbs | Location | OS | S^3 | Done | Done | PkO already confirmed this.
11 | mm | Multimedia | OS | S^3 | Done | Done | PkO already confirmed this.
12 | networkingsrv | Data communication | OS | S^3 | Done | Done | PkO has responded to ensure 100% within S^3, wk 51: PkO has confirmed this
13 | osrndtools | Tools | OS | S^3 | Still work in progress |  | PkO aims to complete this by Q4/2009
14 | ossrv | openservices???? | OS | S^3 | Done | Done | Its been agreed that this is still a Wk 52 2009 target. Wk 51: PkO has confirmed this now.
15 | persistentdata | OS Base services | OS | S^3 | Done | Done | PkO already confirmed this. | written kirill anyway...
16 | security | security | OS | S^3 | Done | Done | Pko already confirmed this.
17 | bt(was part of shortlinksrv) | device connectivity | OS | S^3 | Still work in progress |  | Pko aims to complete this by Q4/2009
18 | usb (was part of shortlinksrv) |  | OS | S^3 | Done |  | Pko aims to complete this by wk46, wk 47 update: There are some issues in the hw and PkO is resolving them. Wk50: Will hear further updates next week. Wk 51: Crazy scheduler done based validation done.
19 | NFC (new pk add into shortlinksrv) |  | OS | S^3 |  |  | wk 50: Have contacted Mikko. Response awaited
20 | text andloc | UI | OS | S^3 | Done | Done | PkO aims to complete this by wk48: Wk 50: Asked for updates from package owners, wk51: Pinged pko again. Change in PkO. No response yet.
21 | unref |  | OS | S^3 | n/a | n/a | This is not a package, but code shared across multiple packages. No SMP related testing needs to be done for this as 'package' using the code will be validated anyway.
22 | wlan | Data communication | OS | S^3 | Done |  | PkO expects this to get over by week 48. Wk: 50: PkO confirms that crazy scheduler based validation is now over. Hw based testing is only planned for spring 2010. Wk 51: Have informed pko about early feb 2010 for S^3 deadline
23 | xmlsrv | Runtimes | OS | S^3 | Done | Done | xmlsecurityengine is pending . PkO has assured validation before Q4/2009. Wk 51: Pinged Pko for a response. Only one component is pending. Wk 51: PkO has confirmed
24 | accesssec | Data communications | MW | S^4 | Still work in progress |  | Q1/2010
25 | appinstall | Runtimes | MW | S^3 | Done |  | PkO expects this to get over by week 47. Wk 50: have asked for updates. Wk51: Software based validation done. Hw based validation pending.
26 | appsupport |  | MW | S^3 | Still work in progress |  | PkO expects this to get over by week 50. wk51: Contacted pko for a response.
27 | btservices | Device connectivity | MW | S^3 | Still work in progress |  | PkO owner aims to achieve this by week 52
28 | camerasrv | Multimedia applications | MW | S^4 |  |  | PkO is unaware until now. Hasnt responded to reminders, Nov 17th : Written about the SMP proposal and referred to Mark Hambleton. Wk 50: Pko will get back next week. Wk51: Pinged package owner again.
29 | classicui | UI | MW | S^4 | n/a | n/a | PkO is unaware until now. Hasnt responded to reminders. Wk 51: Pk will be deprecated from S^4
30 | dlnasrv | Device connectivity | MW | S^4 |  |  | PkO confirms this to be a S^4 target
31 | drm | Security | MW | S^3 | Still work in progress |  | PkO expects this to get over by week 47: wk 50 - have asked pko for status wk51: Pko confirms crazy scheduler based validation nearly complete. Hw based validation pending.
32 | gsprofilesrv |  | MW | S^4 |  |  | PkO confirms this to be a S^4 target
33 | hapticsservices | UI | MW | S^4 |  |  | PkO is unaware until now. Wk47: Referred to MH/ Nokia for plans. Wk 51: Have contacted for plans/progress/status
34 | helix | ?????? | MW | S^3 | Done |  | PkO expects this to get over by week 50, wk 51: contacted pko for an update.
35 | homescreensrv | UI | MW | S^4 | still work in progress | wk51: Was S^3 earlier, now targeted for S^4 | PkO reckons this package wont be affected by SMP plans. Wk51: PkO has confirmed this package is now targeted for S^4 and not S^3. Validation plans, if any, are being worked out.
36 | imghandling | Multimedia | MW | S^3 | Done |  | PkO has confirmed this. Wk51: Hw based validation still pending and not yet planned.
37 | imsrv | Productivity | MW | S^3 | Still work in progress |  | PkO expects this to get over by week 47, wk 50: have asked pko for status, wk51: Sent a reminder again
38 | inputmethods | UI | MW | S^4 | Still work in progress |  | Pko expects this to be a S^4 target, timelines unknown. Response sought from PkO.
39 | ipappprotocols | Data communications | MW | S^3 | Done | Done | PkO has confirmed this
40 | ipappsrv | Personal Comms | MW | S^4 |  |  | Pko is unaware until now, has been referred to the proposal. Wk50: Pinged pkO for a response.
41 | ipconnmgmt | Data communications | MW | S^4 | Done |  | Pko unwilling to commit dates, expects this to get over by Q1 2010. Wk51: crazyscheduler validation done. Hw validation pending.
42 | legacypresence | Productivity | MW | S^4 |  |  | PkO has ruled out S^3, tentative on S^4. Confirmation awaited. Wk51: This is a S^4 target and pko is now making plans on validation. Time frames unknown.
43 | locationsrv | Location | MW | S^3 | Still work in progress |  | Pko expects this to get over by wk52. Wk50: Asked for an update. Response pending.
44 | mds | Multimedia | MW | S^3 | Done |  | Wk50: Sw based validation done. Hw validation pending.
45 | messagingmw | Productivity | MW | S^4 | Still work in progress |  | PkO identified and contacted, 5th Nov - reminder sent. Wk50: Pinged pko again.
46 | metadatasrv | Multimedia | MW | S^3 | Done |  | Pko has already confirmed this Wk51: PkO is yet to plan hw based validation.
47 | mmappfw | Multimedia | MW | S^4 | Still work in progress |  | Pko has no specific time frame info wk51: Contacted pkO for updates.
48 | mmmw | Multimedia | MW |  |  |  | Pko has been contacted again... No update yet. Wk 50: contacted pko again.
49 | mmuifw | Multimedia | MW | S^4 |  |  | Pko unaware of SMP plans, have referred to proposal doc. Response awaited. Reminders sent once again. Wk51: No response from PkO. Have asked for updates once again.
50 | netprotocols | Data communications | MW | S^3 | Done | Done | PkO has confirmed this
51 | networkingdm | Device management | MW | S^3 | Done |  | PkO has confirmed this. Wk 50: hw based validation pending. In touch with Pko.
52 | opensrv | Productivity | MW | S^4 | work in progress |  | Q1/2010
53 | phonesrv | Personal Comms | MW |  |  |  | PkO sent reminder once again, wk 48: Package owner on holidays. Wk 50: Package owner seeks support from community.(?) for this activity. Wk51: Have referred to MH/Nokia.
54 | remoteconn | Device connectivity | MW | S^4 | Done | Done | Week 48, wk 50: PkO has confirmed SMP Safe. Hardware validation happening.
55 | remotemgmt | Device management | MW | S^3 | Done | Done | PkO aims to complete this by H2/2009
56 | remotestorage | Device connectivity | MW | S^4 | N/A - pk to be deprecated | N/A - pk to be deprecated | Week 48, wk 50: PkO reckons package might be dropped from TB10.1
57 | securitysrv | Security | MW | S^3 | Done |  | PkO has confirmed this wk50: hw validation pending
58 | srvdiscovery |  | MW | S^4 | Done | Done | Pko expects this to happen by week 48 and on TB 10.1, Wk 50: PkO confirms as completed
59 | platformtools |  | MW |  | Still work in progress |  | Awaiting confirmation from PkO that SMP Safe may not apply for this package/tool
60 | shortlinkconn | Device connectivity | MW | S^3 | Still work in progress |  | Week 52 is the target
61 | svgt | UI | MW | S^4 |  |  | PkO is unaware until now, pinged for feedback again. Wk 50: PkO changed recently. Have contacted Pko
62 | uiaccelerator | UI | MW | S^4 |  |  | PkO is unaware until now, pinged for feedback again. Wk 50: PkO changed recently. Have contacted Pko
63 | uiresources | UI | MW | S^4 |  |  | PkO is unaware until now. Hasnt responded to reminders. Nov 17th : Steven Yao-PkO has asked for H/W to validate. Have referred to MH/Nokia. Wk51: No updates yet. Contacted again.
64 | uitools | Tools | MW | S^3 | n/a | n/a | PkO confirms all this to be Linux / Windows tools and hence not necessary to be SMP Safe.
65 | usbservices | Device connectivity | MW | S^3 | Done |  | Pko aims this to be Week 46/09 target. Wk50: Hw validation pending
66 | videoutils | Multimedia | MW | S^5 |  |  | Pko unaware of SMP plans, have referred to proposal doc. Wk 48: Had told pkO about ensuring SMPSafe for S^4 release, as this one's a MW pk.
67 | vpnclient | Data communications | MW | S^3 | Still work in progress |  | PkO aims to complete this by Q4/2009
68 | websrv | Runtimes | MW | S^3 | Done | Done | PkO confirms this and SMP Safe code to be made available as early as week 45
69 | wirelessacc | Data communications | MW | S^3 | 2H/2009 |  | PkO yet to confirm.. Response awaited.
70 | devicectrl |  | APP | S^3 | Done | Done | Pko expects this to happen by Q4/2009
71 | commonemail |  | APP |  |  |  | Pko contacted. Response awaited, wk 50: PkO has been pinged again
72 | camera |  | APP |  |  |  | Pko contacted. Response awaited, wk: 50: PkO will get back next week.
73 | conntools |  | APP | S^4 | Done |  | Pko contacted. Response awaited: wk 49: This package may not need to be SMP Safe'ed. PkO yet to confirm. Wk: Pko has confirmed that this will be SMP Safe for S^4 due to a dependency of this tool for other package testing. Wk51: Hw based validation pending
74 | contacts |  | APP | S^4 | work in progress |  | PKO confirms this is wk18/2010 target
75 | contentcontrol |  | APP | S^4 | work in progress |  | PkO will provide details on schedule eventually
76 | conversations |  | APP |  |  |  | Pko contacted. Response awaited, wk 50: PkO has been pinged again
77 | dictionary |  | APP |  |  |  | Package may be deprecated from TB 10.1
78 | files |  | APP | S^4 | work in progress |  | Pko contacted. Response awaited, wk 50: PkO will be rewritten in QT for S^4
79 | gallery |  | APP |  |  |  | No update from PkO, wk 50: pinged pko again for a response.
80 | graphicsuis |  | APP |  |  |  | Pko contacted. Response awaited, wk48: pKO promised to get back by wk 49. Wk 50: Pinged PkO for a response again. Wk51: No response yet. Pinged once again.
81 | helps |  | APP |  |  |  | Pko contacted. Wk 50: PkO needs help and hence has been redirected to contact MH/Nokia for hw support
82 | homescreen |  | APP | S^4 | work in progress |  | Pko contacted. Response awaited, wk 48: PkO is looking for hw to validate SMP Safe. But generally reckons package should be SMP Safe otherwise.
83 | homescreentools |  | APP | S^4 | work in progress |  | Pko contacted. Response awaited, wk 48: PkO is looking for hw to validate SMP Safe. But generally reckons package should be SMP Safe otherwise.
84 | im |  | APP |  |  |  | Pko contacted. Response awaited, wk 50: pinged again for a response
85 | imgeditor |  | APP |  |  |  | Pko contacted. Response awaited, wk 50: pinged again for a response
86 | imgvieweruis |  | APP |  |  |  | Pko contacted. Response awaited, wk 50: pinged again for a response
87 | iptelephony |  | APP |  |  |  | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation.
88 | java |  | APP | S^4 | work in progress, Q1/2010 |  | Q1/2010
89 | speechsrv |  | APP | S^4 | work in progress, lot of work anticipated |  | PkO will provide details on schedule eventually
90 | settingsuis |  | APP | S^4 | work in progress |  | targeted for Q2/2010
91 | utils |  | APP | S^4 | work in progress |  | Pko contacted. Response awaited, wk 50: PkO will be rewritten in QT for S^4
92 | musicplayer |  | APP | S^4 | work in progress |  | H1/2010
93 | voicerec |  | APP | S^4 | work in progress |  | H1/2010
94 | printing |  | APP | S^5 | work in progress |  | Target is too far away to provide deadlines
95 | messaging |  | APP | S^4 | work in progress |  | Q1/2010
96 | organizer |  | APP | S^4 | work in progress
97 | location |  | APP | S^3 | work in progress |  | H2/2009
98 | mmsharinguis |  | APP |  |  |  | PkO unaware of SMP plans.
99 | phone |  | APP |  |  |  | PkO unaware of SMP plans.
100 | photos |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
101 | poc |  | APP |  |  |  | PkO unaware of SMP plans.
102 | videotelephony |  | APP |  |  |  | PkO unaware of SMP plans.
103 | profile |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
104 | radio |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
105 | rndtools |  | APP |  |  |  | Host side tool, need not be SMP Safe validated. PkO to confirm.
106 | screensaver |  | APP |  |  |  | PkO has no idea due to lack of hardware
107 | techview |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
108 | videocenter |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
109 | videoeditor |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
110 | videoplayer |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
110 | videoplayer |  | APP |  |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.

## Tools Integration Plan
Key Features: | [6 empty] | SYMTOOLS ^ B TIMEBOX | [11 empty] | SYMTOOLS ^ C |  | SYMTOOLS ^ D
|  | Package | Key Feature | Description | Bug ID | Misc | wk44 | wk46 | wk 48 | wk50 | wk52 | wk2 | wk4 | wk6 | wk8 | wk10 | wk12 | wk13 | Q2 2010 | Q3 2010 | Q4 2010 | Q1 2011
SYMTOOLS^B | 1 | Build | ROM Tools Linux support | Update BUILDROM, ROMBUILD and ROFSBUILD to build and execute successfully on Linux
| 2 | Build | System Definition v3 | SBS to build the whole package using the package definition file, and avoid running manual build scripts
| 3 | Homescreen tools | Widget specific effects | Widget specific effects | 237
| 4 | Homescreen tools | Background animation | Background animation | 238
| 5 | IDE | RVCT 4.0 support (ARMv7) | Optimised compiler can produce binaries that is significantly smaller and faster. RVCT can also be used to build whole platforms that GCCE cannot. | 513 | Target date unknown
| 6 | Compatability analysis apps | Support for QT APIs | QT support | 1125
| 7 | Compatability analysis apps | Support for Updated Carbide IDE(Eclipse 3.5) |  | 1127
| 8 | test creation / execution fw | Create TEF test module to support running TEF test cases in STIF | merge TEF and STIF | 456
| 9 | test creation / execution fw | add the SymbianUnitTest component to test frameworks package | adding a new unit test component, which will be part of the test solution provided by Symbian Foundation | 458
| 10 | Doc Tools | Code comment extraction to DITA | DITA format is a standard |  | New package
| 11 | Software configuration apps | Carbide.ct | Carbide.ct is a basically a totally new GUI tool that is delivered to SF. It allows users to edit configuration files (confml) with a eclipse based GUI editor. | 1198
SYMTOOLS^C | 12 | Build | TOOLS_WIN32 Platform | A platform that builds windows TOOLS2 binaries regardless of the OS hosting the build, so that I can run the full build on Linux.
| 13 | Device Debug services | Support for Eclipse target communication framework protocol in TRK agent
| 14 | compatability analy mw | Support for QT APIs
| 15 | test creation / execution fw | Integrated Test Environment 1.0 | integrate various test tools as a unified test solution in Carbide. | 460
| 16 | Dynamic analysis apps | Multi-CPU views
| 17 | Dynamic analysis control&capture | Support for kernel components
SYMTOOLS^D | 18 | compatability analysis mw | Introducing automation for testcase execution | Automation is new concept. And also its a long term feature.
| 19 | test creation / execution fw | Integrated Test Environment 2.0 | integrate various test tools as a unified test solution in Carbide. | 461
20
21
22
23
Feature development as planned
Features facing risks
Issues have cropped up

## pending bklog (hidden)
Key? |  | tag
| Wireless_Access/Backlog | Freeway | New Symbian Comms Architecture - A migration to Freeway architecture. |  | 2H/2009 | In development
| Ipappsrv_backlog | NGA | Support for NGA | 2H/2009 | 2H/2009 | In Development.
| Video_Player_Package/Backlog | NGA | Symbian NGA support for video playback Link to feature description | 2009-08-01 | &lt;MCL date&gt; | In development
| VideoTelephony_roadmap | NGA | NGA implemetaion of Video render | 2H/2009 | 2H/2009 | In Development
| Commsfw_Backlog | SMP | SMP | SMP enhanced comms framework | 2010 |  | Proposed
| Graphics_Package/Backlog | SMP | SMP safe - support for multi-core processors |  | 1H/09 (S^3) | In Development
| IP_Connection_Management_Package/Backlog | SMP | Ipconnmgmt SMP-safe: Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Messaging_Package/Backlog | SMP | SMP analysis/ support for messaging |  |  | Proposed
| Vpnclient_Package/Backlog | SMP | SMP safe phase 1 | 2H09 | Planned
| WLAN_Package_Backlog | SMP | SMP safeSupport for multicore processors |  | 2H/09 (SF^3) | Planned
| Wireless_Access/Backlog | SMP | SMP safe verification - Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Access_Security_Package/Backlog | newUI | Implementation of Access Security UIs with Qt | N/A | 2010 1Q | Planned
| Application_Installation_Package/Backlog | newUI | Qt-based AppInstall UI components | Q1 2010 | Q1 2010 | Proposed
| Connectivity_Tools_Package/Backlog | newUI | Qt/Orbit migration for ConnTest | 2H/2009 | 1H/2010 | Proposed
| DRM_Package/Backlog | newUI | Qt-based DRM UI components | Q1 2010 | Q1 2010 | Proposed
yes | IDE_Package/Backlog | newUI | Qt Eclipse integration plugins version 1.5.2 | n/a | Aug 09 | in-progress
| IP_Connection_Management_Package/Backlog | newUI | DirectUI implementation: Orbit implementation of ipconnmgmt UI components. | 2H/2009 | 1H/2010 | Planned
yes | Location_Package/Backlog | newUI | Location UI enhancements with Qt | TBD | TBD | Proposed
yes | Messaging_Package/Backlog | newUI | Conversation based messaging direct touch UI using Qt | 2010-05-01 |  | Ongoing
yes | Phone_backlog | newUI | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | 2H/2009 | 2H/2009 | In Development
yes | Phone_backlog | newUI | Direct UI | 1H/2010 | 1H/2010 | In Development
| Profile_Package/Backlog | newUI | QT'fication of Profiles |  |  | Planned
| Security_Services_Package/Backlog | newUI | Qt-based Securitysrv UI components | Q1 2010 | Q1 2010 | Proposed
yes | VideoTelephony_roadmap | newUI | touch UI support (implementation of common UI API) | 1H/2010 | 1H/2010 | In Development
| Wireless_Access/Backlog | newUI | DirectUI implementation - Orbit (Qt) implementation of wirelessacc UI components. |  | 1H/2010 | Proposed
| Wireless_Access/Backlog | newUI | DirectUI implementation - Replace WLAN Sniffer with Connect Screen. | 2H/2009 | 1H/2010 | Planned

## pdk3.0.d (hidden)
BUG ID | Title | KF | Contrib | Package
575 | Support for files over 2GB | 2GB files | NOKIA | imghandling
587 | Support for over 2GB files | 2GB files | NOKIA | mds
661 | Local Location Based Triggering Enhancements | LBS | NOKIA | Locationserv
245 | Symbian NGA support for video playback Link to feature description | NGA | NOKIA | Video player
268 | Homescreen page management | Multipage HS | NOKIA | HomeScreen
Note on B3: victorp: recieved information that this has been done, checking with package owner when