## Integration Plan
BUG_ID | pdk |  | Feature | TAG | S^N | Main Contributor | Package | IW0935 | IW0937 | IW0939 | IW0941 | IW0943 | IW0945 | IW0947 | IW0949 | IW0953 | xmad | IW1003 | IW1005 | IW1007 | IW1009 | IW1011 | IW1013 | IW1015 | IW1017 | IW1019 | IW1021 | IW1023 | IW1025 | IW1027 | 2010-Q3 | 2010-Q4
246-8 | 2.0.0 |  | Additional Kernel components backport for S^3 to S^2 | N/A | S^2 | DOCOMO/SOSCO | Kernel & Hardware Services |  |  | 0 | [22 empty] | 1
| 3.0.a | -1 | New Comms Framework | 3PC | S^3 | NOKIA | Tech Domain Wide Features |  |  | 0 | [22 empty] | 1
| 3.0.a | -1 | 3PC architecture | 3PC | S^3 | NOKIA | Comms Framework |  |  | 0 | [22 empty] | 1
|  |  | SymbianJ | Java | S^3 | NOKIA | SymbianJ | [15 empty] | 1 | [9 empty] | 1
1339 |  |  | NFC Server | NFC | S^4 | NOKIA | NFC | [25 empty] | 0
1340 |  |  | NFC Lib | NFC | S^4 | NOKIA | NFC | [25 empty] | 0
1341 |  |  | NFC Client | NFC | S^4 | NOKIA | NFC | [25 empty] | 0
906 | 3.0.f |  | volume control | AVRCP1.4 | S^3 | NOKIA | Btservices | [10 empty] | 0 | [14 empty] | 1
1347 | 3.0.f |  | Single click change | Singletap | S^3 | NOKIA | Files | [10 empty] | 0
1349 | 3.0.f |  | Contacts single click compatibility | Singletap | S^3 | NOKIA/IXONOS | Contacts | [8 empty] | 0
1345 | 3.0.f |  | Single Tap in S^3 | Singletap | S^3 | NOKIA | MusicPlayer | [8 empty] | 0
1348 | 3.0.f |  | Single Tap changes to Photos app in S^3. | Singletap | S^3 | NOKIA | Photos | [8 empty] | 0
1368 | 3.0.f |  | 'Single tap contribution' in Homescreen | Singletap | S^3 | NOKIA | Homescreen | [7 empty] | 0
1464 | 3.0.f |  | Single tap in organiser | Singletap | S^3 | NOKIA | Organiser | [7 empty] | 0
1397 | ?? |  | Single Tap in S^3 - Email UI | Singletap | S^3 | NOKIA | commonemail | [13 empty] | 0
739 | 3.0.f |  | Sinlge touch | Singletap | S^3 | NOKIA | ClassicUI | [7 empty] | 0
1451 | N/a |  | Make Qt 4.6.0 available to SF | NewUI | S^3 | NOKIA | QT | [8 empty] | 0
1468 | ?? |  | Make QT 4.6.1 available to SF | NewUI | S^3 | NOKIA | QT | [14 empty] | 0
266 | 3.0.e |  | Homescreen page switching API | Multipage HS | S^3 | NOKIA | HomeScreen | [6 empty] | 0 | [18 empty] | 1
267 | 3.0.e |  | Homescreen mode switching API | Multipage HS | S^3 | NOKIA | HomeScreen | [6 empty] | 0 | [18 empty] | 1
268 | 3.0.d |  | Homescreen page management | Multipage HS | S^3 | NOKIA | HomeScreen | [5 empty] | 0 | [19 empty] | 1
208 | 3.0.g |  | CalDav for single calendar | CalDav | S^3 | SUN | Organiser | [11 empty] | 0 | [13 empty] | 1
496 | 3.0.g |  | CalDav for Multiple Calendar | CalDav | S^3 | SUN | Organiser | [11 empty] | 0 | [13 empty] | 1
495 | 3.0.g |  | Multiple Calendar | CalDav | S^3 | NOKIA | Organiser | [11 empty] | 0 | [13 empty] | 1
599 | 3.0.f |  | RT+ Artist and Title support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [17 empty] | 1
600 | 3.0.f |  | RT+ Web support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [17 empty] | 1
601 | 3.0.f |  | Music Store support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [17 empty] | 1
565 | 3.0.e |  | Dialog reduction: A number of connection dialogs are removed from the software for better user experience. | dialog redux | S^3 | NOKIA | ipconmanagement | [5 empty] | 0 |  | 0 | [17 empty] | 2
438 | 3.0.f |  | Remote contact lookup | lookup | S^3 | NOKIA | Contacts | [8 empty] | 0 | [16 empty] | 1
420 | ?? |  | Music Playback over HDMI | HDMI | S^3 | NOKIA | Musicplayer | [14 empty] | 0 | [10 empty] | 1
466 | 3.0.f |  | Helix engine support for video files > 2GB | 2GB files | S^3 | NOKIA | Helix | [8 empty] | 0 | [16 empty] | 1
575 | 3.0.d |  | Support for files over 2GB | 2GB files | S^3 | NOKIA | imghandling | [5 empty] | 0 | [19 empty] | 1
587 | 3.0.d |  | Support for over 2GB files | 2GB files | S^3 | NOKIA | mds | [5 empty] | 0 | [19 empty] | 1
661 | 3.0.d |  | Local Location Based Triggering Enhancements | LBS | S^3 | NOKIA | Locationserv | [5 empty] | 0 | [19 empty] | 1
219 | N/A |  | Zoom2 Baseport | ExecEnv | S^3 | TI | BSP |  |  |  |  | 0 | [20 empty] | 1
179 | 3.0.d |  | NGA adaptation | NGA | S^3 | NOKIA | Telephony Apps | [5 empty] | 0 | [19 empty] | 1
182 | N/A |  | Basic Non-NGA Graphic Support | NGA | S^3 | NOKIA | Graphics |  |  | inFCL | [22 empty] | 1
235 |  | -1 | PC development platform | NGA | S^4 | NOKIA | Graphics | [25 empty] | 0
181 | 3.0.f | -1 | Graphics surfaces and HW acceleration of graphics | NGA | S^3 | NOKIA | Graphics | [5 empty] | inFCL |  |  |  |  | 0 | [14 empty] | 2
1391 | 3.0.g |  | UI Acceleration migration to OpenWF | NGA | S^3 | NOKIA | UIaccelerator | [11 empty] | 0
237 |  |  | Widget specific effects | NGA | S^3 | NOKIA | HomeScreen | [25 empty] | 0
238 | 3.0.f |  | Homescreen background animation | NGA | S^3 | NOKIA | UIaccelerator | [8 empty] | 0 | [16 empty] | 1
245 | 3.0.d |  | Symbian NGA support for video playback Link to feature description | NGA | S^3 | NOKIA | Video player |  |  |  | 0 | [21 empty] | 1
578 | 3.0.a |  | SMP prototype Kernel | SMP | S^3 | NOKIA | Kernel & Hardware Services |  |  | 0 | [22 empty] | 1
579 | 3.0.a |  | Writeable demand paging | WDP | S^3 | NOKIA | Kernel & Hardware Services |  |  | 0 | [22 empty] | 1
434 |  |  | Contacts application UI revolution using QT | DirectUI | S^4 | NOKIA | Contacts | [22 empty] | 3 |  |  | 1
1470 |  | -1 | Make Qt 4.7 available for Symbian Foundation | DirectUI | S^4 | NOKIA | QT | [22 empty] | 1
|  | -1 | Orbit | DirectUI | S^4 | NOKIA | Uiemo
658 |  |  | Qt Location UI Apps | DirectUI | S^4 | NOKIA | Location
624 |  |  | Conversation based messaging direct touch UI using Qt | DirectUI | S^4 | NOKIA | Messaging
702 |  |  | Implementation of Access Security UIs with Qt | DirectUI | S^4 | NOKIA | accesssec | [18 empty] | 3
560 |  |  | Qt-based Start up animation and splash screen | DirectUI | S^4 | NOKIA | Generic_Applications_Support | [22 empty] | 3 |  |  | 1
826 |  |  | Direct UI | DirectUI | S^4 | NOKIA | Phone | [16 empty] | 3 | [8 empty] | 1
703 |  |  | Deprecation of EAP DB platform APIs and implementation of a new Qt EAP configuration API | DirectUI | S^4 | NOKIA | accesssec | [18 empty] | 3
1510 |  |  | New input UI and framework on QT | DirectUI | S^4 | NOKIA | inputmethods | [23 empty] | 3
1949 |  |  | Direct UI support for Email | DirectUI | S^4 | NOKIA | commonemail | [22 empty] | 3
1986 |  |  | Migrating to Qt | DirectUI | S^4 | Ixonos | Video editor
602 |  |  | QT and Orbit-based Views | DirectUI | S^4 | NOKIA | radio app | [22 empty] | 3
1425 |  |  | Qt UI of Video Telephony | DirectUI | S^4 | NOKIA | Videotelephony | [16 empty] | 3
1572 |  |  | New setting plug-ins for QT version Control panel | DirectUI | S^4 | NOKIA | SettingUI | [22 empty] | 3
1528 |  |  | Homescreen:Basic Orbit based Homescreen | DirectUI | S^4 | NOKIA | Homescreen
1842 |  |  | Basic MO and MT call features with Direct UI | DirectUI | S^4 | NOKIA | Phone | [16 empty] | 3
1845 |  |  | Dialer support with Direct UI | DirectUI | S^4 | NOKIA | Phone | [16 empty] | 3
1874 |  |  | Common UI for CS videotelphony and VideoSharing with Direct UI | DirectUI | S^4 | NOKIA | mmsharinguis | [17 empty] | 3
1880 |  |  | Remove all AVKON dependencies | DirectUI | S^4 | NOKIA | iptelephony | [16 empty] | 3
1881 |  |  | VoIP MO and MT call supoprt with Direct UI | DirectUI | S^4 | NOKIA | phone | [22 empty] | 3
1946 |  | -1 | deprecate the emulator | DirectUI | S^4 | NOKIA | Kernel | [18 empty] | 3
2031 |  |  | Basic Direct UI Camera Application | DirectUI | S^4 | NOKIA | Camera
2048 |  |  | Photos Direct UI implementation using Qt based Orbit library | DirectUI | S^4 | NOKIA | photos | [18 empty] | 3
1588 |  |  | Videoplayer Direct UI implementation using Qt based Orbit library for Symbian^4. | DirectUI | S^4 | NOKIA | Video player | [17 empty] | 3
1110 |  |  | Direct UI support for Bluetooth UI and Bluetooth UI implementation renovation | DirectUI | S^4 | NOKIA | BT services | [23 empty] | 3
2216 |  |  | Migrate new Printing framework UI to Qt | DirectUI | S^4 | NOKIA | Printing
2078 |  |  | DirectUI support for Calendar, Clock and Notes | DirectUI | S^4 | NOKIA | Organizer
2040 |  |  | Image and video quality setting for Direct UI Camera application | DirectUI | S^4 | NOKIA | Camera
2041 |  |  | Exposure and color settings for Direct UI Camera application | DirectUI | S^4 | NOKIA | Camera
zzz
[6 empty] | Package owner MCL bulk contribution |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 2 |  | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Individual Package Contributions
|  |  | IW = integration Window |  | 0 | Done | [8 empty] | 0 | Planned contribution not recieved or not useable
|  |  | IW is a 2 week cycle at the end produces a PDK |  | 1 | Issue: Late or not committed | [8 empty] | 1 | Planned contribution in this time frame
[5 empty] | 2 | At risk | [8 empty] | 2 | Planned contribution recieved
|  |  | BUG_ID - Good engagement with contributor. Timeframe provided |  | 3 | Planned and on track
|  |  | BUG_ID - Engagement with contributor is pending |  | InFCL | FCL Drop Available | [9 empty] | -1 | "Heavy Duty" integration work
|  |  | BUG_ID - too far into the future to start engaging beyond backlog data |  | FCL | FCL Drop planned
Note on S32: victorp: delivery date moved by 2 month
Note on U32: victorp: slip again, in test phase but no clear plan for delivery
Note on D35: victorp: recieved information that this has been done, checking with package owner when
Note on S41: victorp: Not all code in the FCL has made it to the MCL , possible distributionpolicy error in delivery

## Integration Graph
20
Column Labels
| Values | S^4 | Grand Total |  | Values | S^4
| Count of IW1011 |  |  |  | Count of IW1011 | 20
| Count of IW1013 |  |  |  | Count of IW1013 | 20
| Count of IW1015 | 5 | 5 |  | Count of IW1015 | 15
| Count of IW1017 | 2 | 2 |  | Count of IW1017 | 13
| Count of IW1019 | 4 | 4 |  | Count of IW1019 | 9
| Count of IW1021 |  |  |  | Count of IW1021 | 9
| Count of IW1023 |  |  |  | Count of IW1023 | 9
| Count of IW1025 |  |  |  | Count of IW1025 | 9
| Count of IW1027 | 7 | 7 |  | Count of IW1027 | 2
| Count of 2010-Q3 | 2 | 2 |  | Count of 2010-Q3 | 0
| Count of 2010-Q4 |  |  |  | Count of 2010-Q4 | 0
|  | 1 | 41 | 42
Column Labels
| Values | S^2 | S^3 | Grand Total |  |  | Values | S^2 | S^3 | Grand Total
| Count of IW0935 | [5 empty] | Count of IW0935 | 1 | 41
| Count of IW0937 | [5 empty] | Count of IW0937 | 1 | 41
| Count of IW0939 | 1 | 5 | 6 |  |  | Count of IW0939 | 0 | 36
| Count of IW0941 |  | 1 | 1 |  |  | Count of IW0941 |  | 35
| Count of IW0943 |  | 1 | 1 |  |  | Count of IW0943 |  | 34
| Count of IW0945 |  | 7 | 7 |  |  | Count of IW0945 |  | 27
| Count of IW0947 |  | 2 | 2 |  |  | Count of IW0947 |  | 25
| Count of IW0949 |  | 7 | 7 |  |  | Count of IW0949 |  | 18
| Count of IW0953 |  | 7 | 7 |  |  | Count of IW0953 |  | 11
| Count of IW1003 |  | 3 | 3 |  |  | Count of IW1003 |  | 8
| Count of IW1005 |  | 4 | 4 |  |  | Count of IW1005 |  | 4
| Count of IW1007 | [5 empty] | Count of IW1007 |  | 4
| Count of IW1009 |  | 1 | 1 |  |  | Count of IW1009 |  | 3
| Count of IW1011 |  | 2 | 2 |  |  | Count of IW1011 |  | 1
| Count of IW1013 |  | 1 | 1 |  |  | Count of IW1013 |  | 0
| Count of 2010-Q3 | [5 empty] | Count of 2010-Q3
| Count of 2010-Q4 | [5 empty] | Count of 2010-Q4
| Non-SMP Safe SW | SMP SAFE SW Validated | Count N/A
os | 2 | 20 | 2 |  | 24
mw | 11 | 18 | 17 |  | 46
| Non-SMP Safe HW | SMP SAFE HW Validated | Count N/A
os | 7 | 13 | 4 |  | 24
mw | 27 | 10 | 9 |  | 46
OS | SW | HW
safe | 20 | 13
non-safe | 2 | 7
mw | SW&HW
safe | 18
non-safe | 11

## SMP List
| Done |  |  | S^3 Targets
| Still in progress |  |  | S^4 Targets
| Delayed / PkO unaware |  |  | S^5 Targets
SMP safe Status
| Package | Tech Domain | Layer | SMP Safe in Release | S/w based validation (Crazy scheduler) | H/w based validation (naviengine / bridge) | Comments
1 | boardsupport | OS Base services | OS | S^3 | Done | n/a | Emulator BSP - SMP validated for S^3, HAI - wont be affected by SMP Safe as per PkO
2 | buildtools | Tools | OS | S^3 | Done | n/a | Build tools are host side and hence h/w testing is not applicable.
3 | cellularsrv | Personal comms | OS | S^3 | Done | Delayed until H1/2010 | Except for CTSY, PkO aims to complete this by Q4. Wk 51: Pinged PkO for response wk2: insufficient multicore h/w maturity -pko aims to get this done by Q1/2010. Wk 11: PkO targets only by H1/ 2010
4 | commsfw | Data communication | OS | S^3 | Done | Done | PkO already confirmed this.
5 | deviceplatformrelease | Device Management | OS | S^3 | n/a | n/a | As per William Robert, SMP Safe may not apply for this package as its on the host side.
6 | devicesrv | OS Base services | OS | S^3 | Done | No updates on this | SW related components already validated for S^3, HW related components pending. Timeframe to be made available shortly. 4th Nov: PkO has written that h/w validation is targeted only by Q1/2010. Have asked for further clarification and notified about TB9.2 deadline. 16th Nov: PkO has been referred to MH/Nokia for h/w testing. Wk 51: Pinged pko again to ensure this happens within S^3 window. wk2: PkO has not responded despite reminders, Week 6: Have written Arun Varghese again. Expected completion date only by Q1 2010. wk 11: Pinged for Pko update. cc'ed MarkW
7 | graphics | UI | OS | S^3 | Done | Done | Faisal Memon, the new PkO has already confirmed this.
8 | imagingext | Multimedia | OS | S^3 | Done | Delayed | PkO aims to complete this by wk 48, Wk 50: Asked for updates from package owners, updates are coming by for individual components. Have asked PkO to respond for the comp package. PkO has promised to come back by end of week 50. week 51: only one component validation pending - jan 4th week target, wk 6: Have written Pranav Mishra again. wk 8: Updates are coming in parts. However, for some of the components only . emulator based testing has been done. wk 11: pinged pko for update - update pending still.
9 | kernelhwsrv | OS Base services | OS | S^3 | Done | Done | PkO already confirmed this.
10 | lbs | Location | OS | S^3 | Done | Done | PkO already confirmed this.
11 | mm | Multimedia | OS | S^3 | Done | Done | PkO already confirmed this.
12 | networkingsrv | Data communication | OS | S^3 | Done | Done | PkO has responded to ensure 100% within S^3, wk 51: PkO has confirmed this
13 | osrndtools | Tools | OS | S^3 | Done | Done | PkO aims to complete this by Q4/2009, wk2: No updates from PkO yet. Wk 6: Pinged Matti Laitinen for an update.
14 | ossrv | openservices???? | OS | S^3 | Done | Done | Its been agreed that this is still a Wk 52 2009 target. Wk 51: PkO has confirmed this now.
15 | persistentdata | OS Base services | OS | S^3 | Done | Done | PkO already confirmed this. | written kirill anyway...
16 | security | security | OS | S^3 | Done | Done | Pko already confirmed this.
17 | bt(was part of shortlinksrv) | device connectivity | OS | S^3 | Done | Done | Pko aims to complete this by Q4/2009 wk2: PkO still validating. Wk 6: Pinged Pko for confirmation
18 | usb (was part of shortlinksrv) |  | OS | S^3 | Done | Delayed until Wk 35 | Wk16: Now planned for Wk 35
19 | NFC (new pk add into shortlinksrv) |  | OS | S^4 |  |  | wk 50: Have contacted Mikko. Response awaited
20 | text andloc | UI | OS | S^3 | Done | Done | PkO aims to complete this by wk48: Wk 50: Asked for updates from package owners, wk51: Pinged pko again. Change in PkO. No response yet.
21 | unref |  | OS | S^3 | n/a | n/a | This is not a package, but code shared across multiple packages. No SMP related testing needs to be done for this as 'package' using the code will be validated anyway.
22 | wlan | Data communication | OS | S^3 | Done | Delayed | PkO expects this to get over by week 48. Wk: 50: PkO confirms that crazy scheduler based validation is now over. Hw based testing is only planned for spring 2010. Wk 51: Have informed pko about early feb 2010 for S^3 deadline. Wk 7: Package owner confirms lack of hardware.
23 | xmlsrv | Runtimes | OS | S^3 | Done | Done | xmlsecurityengine is pending . PkO has assured validation before Q4/2009. Wk 51: Pinged Pko for a response. Only one component is pending. Wk 51: PkO has confirmed
24 | accesssec | Data communications | MW | S^4 | Still work in progress |  | Q1/2010
25 | appinstall | Runtimes | MW | S^3 | Done | Done | PkO expects this to get over by week 47. Wk 50: have asked for updates. Wk51: Software based validation done. Hw based validation pending. Wk 6: Done Done
26 | appsupport |  | MW | S^3 | Still work in progress |  | PkO expects this to get over by week 50. wk51: Contacted pko for a response. Wk2: pinged Subani (pko) again, wk 11: pinged again
27 | btservices | Device connectivity | MW | S^3 | Done | wk 26 | PkO owner aims to achieve this by week 52. wk2: Pinged sander again for a response.
28 | camerasrv | Multimedia applications | MW | S^4 |  |  | PkO is unaware until now. Hasnt responded to reminders, Nov 17th : Written about the SMP proposal and referred to Mark Hambleton. Wk 50: Pko will get back next week. Wk51: Pinged package owner again. Wk 6: written teemu on S^4 targets. wk7: Teemu has no SMP requirements on his backlog
29 | classicui | UI | MW | S^4 | n/a | n/a | PkO is unaware until now. Hasnt responded to reminders. Wk 51: Pk will be deprecated from S^4
30 | dlnasrv | Device connectivity | MW | S^4 | n/a | n/a | Wk 16: Pk may not be part of S^4.
31 | drm | Security | MW | S^3 | Still work in progress |  | PkO expects this to get over by week 47: wk 50 - have asked pko for status wk51: Pko confirms crazy scheduler based validation nearly complete. Hw based validation pending. Wk2: Written a mail to Simo wk 4, wk 8: no response from PkO, wk 11: pinged again
32 | gsprofilesrv |  | MW | S^4 | wk 26 |  | Wk 16: PkO confirms wk 26 target
33 | hapticsservices | UI | MW | S^4 |  |  | PkO is unaware until now. Wk47: Referred to MH/ Nokia for plans. Wk 51: Have contacted for plans/progress/status. Wk2: reminded package owner.. Wk 6: PkO is still 'unaware of SMP' plans !!!
34 | helix | ?????? | MW | S^4 | Done | No access to hardware | Wk 16: No access to hardware and hence no commits on deadline.
35 | homescreensrv | UI | MW | S^4 | still work in progress | wk51: Was S^3 earlier, now targeted for S^4 | PkO reckons this package wont be affected by SMP plans. Wk51: PkO has confirmed this package is now targeted for S^4 and not S^3. Validation plans, if any, are being worked out. Wk 5: now rescheduled to S^4
36 | imghandling | Multimedia | MW | S^3 | Done | No access to hardware, timeframes unknown | Wk 16: No access to hardware and hence no commits on deadline.
37 | imsrv | Productivity | MW | S^3 | Still work in progress | No access to hardware | PkO expects this to get over by week 47, wk 50: have asked pko for status, wk51: Sent a reminder again, wk2: have pinged Pko wk 7: pinged again, wk 11: pinged again
38 | inputmethods | UI | MW | S^4 |  |  | Wk 16: PkO has no SMP plans. Further discussions in progress.
39 | ipappprotocols | Data communications | MW | S^3 | Done | Done | PkO has confirmed this
40 | ipappsrv | Personal Comms | MW | S^4 |  |  | Pko is unaware until now, has been referred to the proposal. Wk50: Pinged pkO for a response. Wk 6: Pinged Paulius again for any updates
41 | ipconnmgmt | Data communications | MW | S^4 | Done | No access to hardware, timeframes unknown | Pko unwilling to commit dates, expects this to get over by Q1 2010. Wk51: crazyscheduler validation done. Hw validation pending. Wk 7: Package owner does not intend to take up hw validation in the next few months
42 | legacypresence | Productivity | MW | S^4 |  |  | PkO has ruled out S^3, tentative on S^4. Confirmation awaited. Wk51: This is a S^4 target and pko is now making plans on validation. Time frames unknown.
43 | locationsrv | Location | MW | S^3 | Done | Done | Pko expects this to get over by wk52. Wk50: Asked for an update. Response pending. Wk 7: pinged pko confirms this is done
44 | mds | Multimedia | MW | S^3 | Done | No access to hardware | Wk 16: No access to hardware and hence no commits on deadline.
45 | messagingmw | Productivity | MW | S^4 | Still work in progress |  | PkO identified and contacted, 5th Nov - reminder sent. Wk50: Pinged pko again.
46 | metadatasrv | Multimedia | MW | S^3 | Done |  | Wk 16: No access to hardware and hence no commits on deadline.
47 | mmappfw | Multimedia | MW | S^4 | Still work in progress |  | Pko has no specific time frame info wk51: Contacted pkO for updates.
48 | mmmw | Multimedia | MW | S^4 |  |  | Pko has been contacted again... No update yet. Wk 50: contacted pko again.
49 | mmuifw | Multimedia | MW | S^4 |  |  | Pko unaware of SMP plans, have referred to proposal doc. Response awaited. Reminders sent once again. Wk51: No response from PkO. Have asked for updates once again.
50 | netprotocols | Data communications | MW | S^3 | Done | Done | PkO has confirmed this
51 | networkingdm | Device management | MW | S^3 | Done | n/a | PkO has confirmed this. Wk 50: hw based validation pending. In touch with Pko. Merged with the remote mgmt package
52 | opensrv | Productivity | MW | S^4 | n/a | n/a | Pk will be deprecated
53 | phonesrv | Personal Comms | MW | S^4 |  |  | PkO sent reminder once again, wk 48: Package owner on holidays. Wk 50: Package owner seeks support from community.(?) for this activity. Wk51: Have referred to MH/Nokia. Wk 7: Pinged Paulius and still no change in updates.
54 | remoteconn | Device connectivity | MW | S^4 | Done | Done | Week 48, wk 50: PkO has confirmed SMP Safe. Hardware validation happening. Pko confirms hw validation done
55 | remotemgmt | Device management | MW | S^3 | Done | Done | PkO aims to complete this by H2/2009. Also includes networkingdm package
56 | remotestorage | Device connectivity | MW | S^4 | n/a | n/a | Week 48, wk 50: PkO reckons package might be dropped from TB10.1
57 | securitysrv | Security | MW | S^3 | Done | Done | PkO has confirmed this wk50: hw validation pending, wk 7: pko update pending, Done -Done
58 | srvdiscovery |  | MW | S^4 | Done | Done | Pko expects this to happen by week 48 and on TB 10.1, Wk 50: PkO confirms as completed
59 | platformtools |  | MW |  | n/a | n/a | Awaiting confirmation from PkO that SMP Safe may not apply for this package/tool
60 | shortlinkconn | Device connectivity | MW | S^3 |  |  | Week 52 is the target, target revised. End of February, wk 7: pinged dale self
61 | svgt | UI | MW | S^4 |  |  | Wk 16: PkO unwilling to commit deadline.
62 | uiaccelerator | UI | MW | S^4 |  |  | Wk16: PkO unwilling to comment on SMP Plans, but reckons Pk is generally SMP Safe
63 | uiresources | UI | MW |  | n/a | n/a | PkO is unaware until now. Hasnt responded to reminders. Nov 17th : Steven Yao-PkO has asked for H/W to validate. Have referred to MH/Nokia. Wk51: No updates yet. Contacted again. Pk will be deprecated since part of avkon
64 | uitools | Tools | MW | S^3 | n/a | n/a | PkO confirms all this to be Linux / Windows tools and hence not necessary to be SMP Safe.
65 | usbservices | Device connectivity | MW | S^3 | Done |  | Pko aims this to be Week 46/09 target. Wk50: Hw validation pending
66 | videoutils | Multimedia | MW | S^4 | n/a | n/a | Pko unaware of SMP plans, have referred to proposal doc. Wk 48: Had told pkO about ensuring SMPSafe for S^4 release, as this one's a MW pk. Wk 8: Pk owner reckons that this package may not be used/necessary in S^4. and hence doesnt plan for validation
67 | vpnclient | Data communications | MW | S^3 |  |  | Wk 16: PkO unwilling to commit deadline.
68 | websrv | Runtimes | MW | S^3 | Done | Done | PkO confirms this and SMP Safe code to be made available as early as week 45
69 | wirelessacc | Data communications | MW | S^3 | 2H/2009 | No access to hardware, timeframes unknown | PkO yet to confirm.. Response awaited. Wk 4, wk 7: pko update pending, Pko does not intend to complete validation activity for the next few months
70 | devicectrl |  | APP | S^3 | Done | Done | Pko expects this to happen by Q4/2009
71 | commonemail |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk 50: PkO has been pinged again
72 | camera |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk: 50: PkO will get back next week.
73 | conntools |  | APP | S^4 | Done | H2 2010 | Wk 16: No access to hardware and hence not before H2 2010
74 | contacts |  | APP | S^4 | wk18 | wk18 | PKO confirms this is wk18/2010 target
75 | contentcontrol |  | APP | S^4 |  |  | PkO will provide details on schedule eventually
76 | conversations |  | APP | S^4 | n/a | n/a | conversations package will be deprecated from S^4
77 | dictionary |  | APP |  | n/a | n/a | Package may be deprecated from TB 10.1
78 | files |  | APP | S^4 | work in progress |  | Wk 16: Week 26 is the target now.
79 | gallery |  | APP |  | n/a | n/a | No update from PkO, wk 50: pinged pko again for a response. , pk will be deprecated
80 | graphicsuis |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk48: pKO promised to get back by wk 49. Wk 50: Pinged PkO for a response again. Wk51: No response yet. Pinged once again.
81 | helps |  | APP |  | n/a | n/a | Pko contacted. Wk 50: PkO needs help and hence has been redirected to contact MH/Nokia for hw support - package will be deprecated from S^4
82 | homescreen |  | APP | S^4 | work in progress |  | Pko contacted. Response awaited, wk 48: PkO is looking for hw to validate SMP Safe. But generally reckons package should be SMP Safe otherwise.
83 | homescreentools |  | APP | S^4 | work in progress |  | Pko contacted. Response awaited, wk 48: PkO is looking for hw to validate SMP Safe. But generally reckons package should be SMP Safe otherwise.
84 | im |  | APP |  | n/a | n/a | This package will be merged into imsrv from S^4
85 | imgeditor |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk 50: pinged again for a response , contacted ixonos
86 | imgvieweruis |  | APP |  | n/a | n/a | Pko contacted. Response awaited, wk 50: pinged again for a response, pk will be deprecated from S^4
87 | iptelephony |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation. Wk 7: pinged paulius and no change in status
88 | java |  | APP | S^5 | ??? | ??? | Wk 16: Pk confirms S^5 target. Discussing with them about Nokia SMP proposal deadlines.
89 | speechsrv |  | APP | S^4 | n/a | n/a | PkO will provide details on schedule eventually, wk7: pk will be dropped from S^4, availability on future Symbian platforms to be decided eventually
90 | settingsuis |  | APP | S^4 | Q2 | Q2 | targeted for Q2/2010
91 | utils |  | APP | S^4 | n/a | n/a | wk 16 update: No plan to release this in S^4. Plans beyond that are unknown presently.
92 | musicplayer |  | APP | S^4 | work in progress |  | H1/2010
93 | voicerec |  | APP | S^4 | work in progress |  | H1/2010, wk 8: pinged package owner for an update on this.
94 | printing |  | APP | S^4 | n/a | n/a | Package is dropped from TB 10.1
95 | messaging |  | APP | S^4 | work in progress |  | Q1/2010
96 | organizer |  | APP | S^4 | work in progress |  | Wk16: PkO has no SMP plans. Further discussions in progress
97 | location |  | APP | S^3 | Done | Done | end of feb , wk 8: pinged pko. Pko confirms done-done
98 | mmsharinguis |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation. Wk 7: pinged paulius and no change in status
99 | phone |  | APP | S^4 |  |  | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation. Wk 7: pinged paulius and no change in status
100 | photos |  | APP | S^4 |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
101 | poc |  | APP | S^4 |  |  | PkO unaware of SMP plans. Wk 8: pinged pko for a response
102 | videotelephony |  | APP | S^4 |  |  | PkO unaware of SMP plans. Wk 8: pinged pko for a response
103 | profile |  | APP | S^4 |  |  | Wk 16: PkO has no SMP plans. Further discussions in progress.
104 | radio |  | APP | S^4 |  |  | Wk16: PkO unable to commit deadlines. Will take up SMP activity shortly.
105 | rndtools |  | APP | S^4 | n/a | n/a | Host side tool, need not be SMP Safe validated. PkO to confirm.
106 | screensaver |  | APP |  | n/a | n/a | Hardware availability issues - written to Mark Hambleton/Nokia - package will be deprecated from S^4
107 | techview |  | APP | S^4 |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again., New package owner : no response yet, wk 8: pinged package owner
108 | videocenter |  | APP |  | n/a | n/a | Pkg will be deprecated from S^4
109 | videoeditor |  | APP | S^4 |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again. Wk 5/7: Contacted ixonos
110 | videoplayer |  | APP | S^4 |  |  | PkO yet to respond: Wk 50: sent out a reminder to PkO again. Wk 2, wk 6, wk 8: pinged package owner for updates
APP

## Tools Integration Plan
Key Features: | [6 empty] | SYMTOOLS ^ B TIMEBOX | [11 empty] | SYMTOOLS ^ C | [7 empty] | SYMTOOLS ^ D
|  | Package | Key Feature | Description | Bug ID | Misc | wk44 | wk46 | wk 48 | wk50 | wk52 | wk2 | wk4 | wk6 | wk8 | wk10 | wk12 | wk13 | wk15 | wk17 | wk19 | wk21 | wk23 | wk25 | wk27 | Q3 2010 | Q4 2010 | Q1 2011
SYMTOOLS^B | 1 | Build | ROM Tools Linux support | Update BUILDROM, ROMBUILD and ROFSBUILD to build and execute successfully on Linux
| 2 | Build | System Definition v3 | SBS to build the whole package using the package definition file, and avoid running manual build scripts
| 3 | Homescreen tools | Background animation | Background animation | 238
| 4 | IDE | RVCT 4.0 support (ARMv7) | Optimised compiler can produce binaries that is significantly smaller and faster. RVCT can also be used to build whole platforms that GCCE cannot. | 513 | Target date unknown
| 5 | Compatability analysis apps | Support for QT APIs | QT support | 1125
| 6 | Compatability analysis apps | Support for Updated Carbide IDE(Eclipse 3.5) |  | 1127
| 7 | test creation / execution fw | Create TEF test module to support running TEF test cases in STIF | merge TEF and STIF | 456
| 8 | test creation / execution fw | add the SymbianUnitTest component to test frameworks package | adding a new unit test component, which will be part of the test solution provided by Symbian Foundation | 458
| 9 | Doc Tools | Code comment extraction to DITA | DITA format is a standard |  | New package
| 10 | Software configuration apps | Carbide.ct | Carbide.ct is a basically a totally new GUI tool that is delivered to SF. It allows users to edit configuration files (confml) with a eclipse based GUI editor. | 1198
SYMTOOLS^C | 11 | Build | TOOLS_WIN32 Platform | A platform that builds windows TOOLS2 binaries regardless of the OS hosting the build, so that I can run the full build on Linux.
| 12 | Device Debug services | Support for Eclipse target communication framework protocol in TRK agent
| 13 | compatability analy mw | Support for QT APIs
| 14 | test creation / execution fw | Integrated Test Environment 1.0 | integrate various test tools as a unified test solution in Carbide. | 460
| 15 | Dynamic analysis apps | Multi-CPU views |  | 715
| 16 | <new package> | Qt Creator/DK beta
| 17 | Software configuration apps | Carbide.c++ 3.0
| 18 | Dynamic analysis control&capture | Support for kernel components
SYMTOOLS^D | 19 | compatability analysis mw | Introducing automation for testcase execution | Automation is new concept. And also its a long term feature.
| 20 | test creation / execution fw | Integrated Test Environment 2.0 | integrate various test tools as a unified test solution in Carbide. | 461
21
22
23
24
Feature development as planned
Features facing risks
Issues have cropped up
Done

## pending bklog (hidden)
Key? |  | tag
| Wireless_Access/Backlog | Freeway | New Symbian Comms Architecture - A migration to Freeway architecture. |  | 2H/2009 | In development
| Ipappsrv_backlog | NGA | Support for NGA | 2H/2009 | 2H/2009 | In Development.
| Video_Player_Package/Backlog | NGA | Symbian NGA support for video playback Link to feature description | 2009-08-01 | &lt;MCL date&gt; | In development
| VideoTelephony_roadmap | NGA | NGA implemetaion of Video render | 2H/2009 | 2H/2009 | In Development
| Commsfw_Backlog | SMP | SMP | SMP enhanced comms framework | 2010 |  | Proposed
| Graphics_Package/Backlog | SMP | SMP safe - support for multi-core processors |  | 1H/09 (S^3) | In Development
| IP_Connection_Management_Package/Backlog | SMP | Ipconnmgmt SMP-safe: Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Messaging_Package/Backlog | SMP | SMP analysis/ support for messaging |  |  | Proposed
| Vpnclient_Package/Backlog | SMP | SMP safe phase 1 | 2H09 | Planned
| WLAN_Package_Backlog | SMP | SMP safeSupport for multicore processors |  | 2H/09 (SF^3) | Planned
| Wireless_Access/Backlog | SMP | SMP safe verification - Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Access_Security_Package/Backlog | newUI | Implementation of Access Security UIs with Qt | N/A | 2010 1Q | Planned
| Application_Installation_Package/Backlog | newUI | Qt-based AppInstall UI components | Q1 2010 | Q1 2010 | Proposed
| Connectivity_Tools_Package/Backlog | newUI | Qt/Orbit migration for ConnTest | 2H/2009 | 1H/2010 | Proposed
| DRM_Package/Backlog | newUI | Qt-based DRM UI components | Q1 2010 | Q1 2010 | Proposed
yes | IDE_Package/Backlog | newUI | Qt Eclipse integration plugins version 1.5.2 | n/a | Aug 09 | in-progress
| IP_Connection_Management_Package/Backlog | newUI | DirectUI implementation: Orbit implementation of ipconnmgmt UI components. | 2H/2009 | 1H/2010 | Planned
yes | Location_Package/Backlog | newUI | Location UI enhancements with Qt | TBD | TBD | Proposed
yes | Messaging_Package/Backlog | newUI | Conversation based messaging direct touch UI using Qt | 2010-05-01 |  | Ongoing
yes | Phone_backlog | newUI | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | 2H/2009 | 2H/2009 | In Development
yes | Phone_backlog | newUI | Direct UI | 1H/2010 | 1H/2010 | In Development
| Profile_Package/Backlog | newUI | QT'fication of Profiles |  |  | Planned
| Security_Services_Package/Backlog | newUI | Qt-based Securitysrv UI components | Q1 2010 | Q1 2010 | Proposed
yes | VideoTelephony_roadmap | newUI | touch UI support (implementation of common UI API) | 1H/2010 | 1H/2010 | In Development
| Wireless_Access/Backlog | newUI | DirectUI implementation - Orbit (Qt) implementation of wirelessacc UI components. |  | 1H/2010 | Proposed
| Wireless_Access/Backlog | newUI | DirectUI implementation - Replace WLAN Sniffer with Connect Screen. | 2H/2009 | 1H/2010 | Planned

## pdk3.0.d (hidden)
BUG ID | Title | KF | Contrib | Package
575 | Support for files over 2GB | 2GB files | NOKIA | imghandling
587 | Support for over 2GB files | 2GB files | NOKIA | mds
661 | Local Location Based Triggering Enhancements | LBS | NOKIA | Locationserv
245 | Symbian NGA support for video playback Link to feature description | NGA | NOKIA | Video player
268 | Homescreen page management | Multipage HS | NOKIA | HomeScreen
Note on B3: victorp: recieved information that this has been done, checking with package owner when